Warehouse Wizard

Hosting and Continuity Options: Cloud and On-Premise

Executive summary Management has set a worst case: the warehouse must keep operating when both the wired and the satellite internet connections are unavailable. Each hosting option is tested against that case and priced at $100 per hour. The requirement is not met today. Warehouse Wizard runs in the cloud, and a device that cannot reach it freezes: it can show its current task but cannot post a putaway, pick, receipt or count. If both internet lines fail, the application stops for the whole building. Hosting Warehouse Wizard on the existing virtual-machine server behind the Barracuda firewall is the only option that keeps electronic operations running inside the building. Updates owed to NetSuite would queue locally and send when the internet returns. Because the database has to be rebuilt from scratch, the estimate is $63,200 to $98,400 to build and $20,000 to $34,400 a year to run. A lower-cost alternative keeps the cloud system and adds a printed downtime kit. It keeps the warehouse moving on paper while the application is down, for $6,400 to $10,400. Recommendation: leadership should first decide, in writing, whether the application itself must keep working with no internet, and for how long. If it must, approve Option 2. If paper operation for a defined period is acceptable, approve Option 1 and revisit Option 2 if that period is exceeded. The two answers differ in cost by roughly a factor of ten.

# 1. Purpose and the scenario

Leadership needs to choose a hosting and continuity approach for Warehouse Wizard as NetSuite comes into service. The options are tested against management's worst-case scenario and priced.

Management's scenario is that both wired and satellite internet are inaccessible and the warehouse must keep operating. Four points are not yet defined, and the estimates depend on them:

Which functions must keep working: the estimates assume in-building receiving, putaway, picking, packing, transfers, counts and label printing.

For how long: the estimates assume days, not hours, because a short loss is already covered by the existing failover.

Whether power, the building network, Wi-Fi, tablets and printers are assumed to keep running: the existing power failover is assumed to cover them; IT to confirm.

What happens to inbound work: with no internet, new orders, customer contact and carrier bookings stop in any option, so continued operation is limited to work already in the building.

# 2. Starting position

The building has wired and satellite internet and power failover.

Warehouse Wizard authenticates to NetSuite with certificate-based machine-to-machine authentication. The connection test passed on 10 October 2026 against the NetSuite sandbox account, and no synchronisation job had run at that date.

NetSuite is the system of record. Warehouse Wizard sends it updates through a job queue that retries failed sends and keeps a record of those that fail.

A device that loses its connection freezes and cannot post work. It keeps its place in the task and resumes after reconnecting. Replay of work queued offline is turned off on purpose, so nothing posts from a stale view of the warehouse.

The backend is a managed cloud platform with 20 server functions. The migration files define about 80 tables, 190 database functions, 200 access policies and 70 triggers (counts include later replacements, so live totals are lower).

# 3. What each option does in the scenario

Option 1 keeps Warehouse Wizard in the cloud and adds a printed downtime kit. Option 2 hosts Warehouse Wizard on the existing VM server as the primary system.

| Situation | Option 1: cloud with downtime kit | Option 2: on-premise primary |
| --- | --- | --- |
| One internet line fails | Continues on the other line. | Continues on the other line. |
| Both lines fail (management scenario) | The application stops across the building. The warehouse continues on printed lists and forms, and the backlog is entered afterwards. | The application continues on the local network. NetSuite updates queue and send on reconnection. Internet-dependent features are unavailable (below). |
| NetSuite unavailable, internet working | NetSuite-dependent work pauses, and queued updates retry. | The same. Hosting location does not change this. |
| Fault in the VM host, local network or building power | Not affected, apart from the paper fallback. | The application is unavailable until the host is restored, unless a second host or tested recovery exists. |
| Everything healthy | Normal. | Normal. |

## What continues and what does not under Option 2

Continues: Receiving, putaway, picking, packing, transfers and counts inside the building; sign-in by password or badge; label printing on the local network; supervisor alerts inside the application; stock positions held locally.

Does not continue: Lookups of NetSuite documents that were not already copied locally; new orders from NetSuite; posting to NetSuite (queued, not lost); email notifications, invitations and password resets; push notifications to tablets; the AI features (assistant, voice transcription, container vision).

Picking would run only against orders received before the outage, so the duration set in Section 1 limits how long any option can keep working.

# 4. The NetSuite connection

NetSuite is a cloud service. In the management scenario it is unreachable under both options, so no option can post to it during the outage. The difference is what the building can do while it waits. Under Option 2 the existing retry queue holds the updates and the warehouse keeps working. Under Option 1 the application stops and the paper kit carries the work.

When the internet returns, queued updates must be sent in the order they were captured, and each must be checked against NetSuite as it then stands, for example a purchase order changed while the building was offline. Conflicts would go to an exception queue for review, not post automatically. This reconciliation is part of the estimate for Option 2 (work packages G and H).

# 5. How Option 2 would be built

The design uses the VM server the business already runs, with the Barracuda firewall as the single controlled boundary. It is a working design that work package A would confirm.

The web application and the backend (database, sign-in, file storage, live updates and the server functions) each get a VM. Tablets connect over the building network to an internal address.

The existing database cannot be moved as it stands. The new one is built from scratch from the live design, loaded with current data and checked against the live system before cutover.

Several services must work with no internet: an internal certificate authority (public certificate renewal needs the internet), local DNS, and a local time source, because audit records depend on accurate time.

NetSuite traffic goes out over HTTPS through the firewall. A local queue runner replaces the scheduled cloud job, and a local copy of NetSuite items, open orders and receiving documents is refreshed while the internet is up. NetSuite callbacks need a controlled path through the firewall, or the system can poll outbound, which NetSuite meters.

The application shows a banner when it is running without internet, explains which features are unavailable, and offers sign-in that needs no email.

The VM host is shared with other workloads. At minimum it needs encrypted nightly backups to a second location with tested restores. A second host or a documented recovery plan is better, and IT would price it.

Power, switches, Wi-Fi access points, tablets and local printers must stay up for the scenario to work. The existing power failover is assumed to cover them; IT to confirm.

Releases deploy to the VMs through a pipeline the company owns. Every database change must be applied to the self-hosted system as well as the development environment.

# 6. Cost

Effort is in working days of 8 hours at $100 per hour ($800 per day), including testing and documentation. The contingency is 25%, higher than the 15% used for the NetSuite integration proposal, because the database rebuild and the no-internet mode rest on assumptions not yet verified. Estimates are budgetary, about 30% either way, and work package A firms them up.

## Option 2: one-time build

| Work package | Low days | High days | Low cost | High cost |
| --- | --- | --- | --- | --- |
| A. Define the continuity requirement; check host capacity, power and network; design VM and firewall rules | 3 | 4 | $2,400 | $3,200 |
| B. Build and harden the VMs; internal certificate authority, local DNS and local time source | 3 | 5 | $2,400 | $4,000 |
| C. Stand up the self-hosted backend (database engine, sign-in, file storage, live updates, function runtime) | 5 | 8 | $4,000 | $6,400 |
| D. Rebuild the database from scratch: extract the current design from the live system, consolidate into a clean baseline, reload reference data, verify against the live system | 8 | 14 | $6,400 | $11,200 |
| E. Move live data across; reconcile counts; rehearse the cutover | 4 | 6 | $3,200 | $4,800 |
| F. Port and retest the 20 server functions; replace or switch off the email, push and AI dependencies | 8 | 12 | $6,400 | $9,600 |
| G. NetSuite link through the firewall; local queue runner and scheduler; local copy of NetSuite items, open orders and receiving documents; callback path | 6 | 9 | $4,800 | $7,200 |
| H. No-internet operating mode: local sign-in, clear status banner, disabled-feature messages, reconciliation and exception queue on reconnection | 6 | 10 | $4,800 | $8,000 |
| I. Repoint web and Android clients; release pipeline to the VMs; keep the development environment in step | 5 | 8 | $4,000 | $6,400 |
| J. Backups with an offline copy, restore testing, monitoring and alerting, clean shutdown on power loss | 4 | 6 | $3,200 | $4,800 |
| K. Security testing, acceptance testing, a simulated internet-loss drill, parallel running, cutover and rollback plan | 8 | 12 | $6,400 | $9,600 |
| L. Runbooks, training and handover | 3 | 4 | $2,400 | $3,200 |
| Subtotal | 63 | 98 | $50,400 | $78,400 |
| Contingency (25%) | 16 | 25 | $12,800 | $20,000 |
| Total one-time | 79 | 123 | $63,200 | $98,400 |

## Option 2: ownership cost per year

| Activity | Low days | High days | Low cost | High cost |
| --- | --- | --- | --- | --- |
| Patching, monitoring and security updates for the VMs and backend | 6 | 10 | $4,800 | $8,000 |
| Deploying releases and applying every database change to the self-hosted system | 8 | 14 | $6,400 | $11,200 |
| Backup verification and a scheduled internet-loss drill | 4 | 6 | $3,200 | $4,800 |
| Upgrades of the self-hosted backend components | 3 | 5 | $2,400 | $4,000 |
| Incident response and support allowance | 4 | 8 | $3,200 | $6,400 |
| Total per year | 25 | 43 | $20,000 | $34,400 |

## Option 2: five-year view

| Item | Low days | High days | Low cost | High cost |
| --- | --- | --- | --- | --- |
| One-time build, with contingency | 79 | 123 | $63,200 | $98,400 |
| Five years of ownership effort | 125 | 215 | $100,000 | $172,000 |
| Total over five years | 204 | 338 | $163,200 | $270,400 |

## Option 1: cloud with downtime kit

| Work package | Low days | High days | Low cost | High cost |
| --- | --- | --- | --- | --- |
| Scheduled export of stock by location and open tasks to a local PC and printer while the internet is up | 3 | 5 | $2,400 | $4,000 |
| Printed forms and a written downtime procedure for receiving, putaway, picking, shipping and counting | 1 | 2 | $800 | $1,600 |
| After-outage re-entry and reconciliation procedure, including NetSuite catch-up | 2 | 3 | $1,600 | $2,400 |
| Subtotal | 6 | 10 | $4,800 | $8,000 |
| Contingency (25%) | 2 | 3 | $1,600 | $2,400 |
| Total one-time | 8 | 13 | $6,400 | $10,400 |

Ownership cost for Option 1 is a yearly drill of the paper procedure, 2 to 3 days ($1,600 to $2,400).

## Not included

Server hardware: assumed nil, provided the VM host has spare capacity. Any expansion, a second host, extra backup storage or off-site backup would be additional.

Operating-system, hypervisor and firewall licences or support changes.

Internal IT time to provision the VMs and change firewall rules.

The current cloud hosting cost, which finance should compare with the annual cost of Option 2.

# 7. Risks of Option 2

A rebuild of this size has a real chance of surprises. The 25% contingency and the parallel run are there for that reason.

The cloud project would remain as the development environment, so every change has to be applied twice, and differences between the two are a standing source of faults.

Fixes reach the floor more slowly than under the managed pipeline.

Patching, backups and incident response become internal duties that depend on a small number of people.

A no-internet mode that is never exercised is likely to fail when it is first needed. The yearly drill in the estimate keeps it working.

The host is shared, so a fault or resource contention on it affects the warehouse directly.

# 8. Options compared

| Option | App works with no internet? | One-time | Per year | Main risk |
| --- | --- | --- | --- | --- |
| 1. Cloud with downtime kit | No. Warehouse runs on paper. | $6,400 to $10,400 | $1,600 to $2,400 | Paper operation is slow and error prone, and the backlog must be entered afterwards. |
| 2. On-premise primary | Yes, inside the building. | $63,200 to $98,400 | $20,000 to $34,400 | Rebuild risk and a permanent ownership burden. |
| 3. Cloud primary with local standby | Possibly. | Feasibility check $2,400 to $4,000; build not priced | Not priced | Depends on whether the managed backend allows continuous copying of its data. Not yet verified. |

Recommendation Decide the requirement before the option. Ask management to confirm in writing which functions must work with no internet, for how long, and with what power and network assumptions. If the application itself must keep running, Option 2 is the only option that does it, and the budget is $63,200 to $98,400 plus $20,000 to $34,400 a year. If paper operation for a defined period is acceptable, Option 1 meets the requirement at about a tenth of the cost, and Option 2 can be revisited if that period proves too short. Decide before more NetSuite integration is built. The queue runner and the local copy of NetSuite data would be built differently under Option 2, so building them first for the cloud may mean rework.

# 9. Decisions and next steps

Leadership defines the continuity requirement in writing: functions, duration, and power and network assumptions.

Leadership chooses Option 1 or Option 2, or authorises the Option 3 feasibility check.

IT confirms spare capacity on the VM host, the hypervisor, current backup coverage, Barracuda support status, and how long power covers the host, network, Wi-Fi and printers.

Finance compares the annual cost of Option 2 with the current cloud hosting cost.

If Option 2 is chosen, start with work package A ($2,400 to $3,200), which confirms the estimate before the larger commitment.

Make the decision before further NetSuite integration work is built.

# Appendix A: Evidence and assumptions

| Statement | Basis | Status |
| --- | --- | --- |
| Wired and satellite internet and power failover exist. | Stated by IT. | Provided |
| Management's worst case is loss of both internet lines. | Stated by management. | Provided |
| Devices freeze offline and cannot post work; offline replay is disabled. | Offline reconnect design (approved 8 July 2026) and the offline queue code. | Confirmed |
| NetSuite authentication is certificate-based; the test passed on 10 October 2026 on the sandbox account; no sync job had run. | Project connection records. | Confirmed |
| NetSuite updates use a retrying job queue with failure records. | NetSuite integration proposal. | Confirmed |
| The backend has 20 server functions. | Repository. | Confirmed |
| Migration files define about 80 tables, 190 functions, 200 policies and 70 triggers. | Repository; counts include later replacements. | Confirmed |
| The database must be rebuilt from scratch. | Stated by IT. | Provided |
| Rate is $100 per hour; a working day is 8 hours. | Rate provided; day length assumed. | Assumption |
| Effort estimates and the 25% contingency. | Author's estimates from the repository, about 30% either way. | Estimate |
| The VM host has spare capacity and runs a hypervisor. | Not checked. | To verify |
| Power covers the host, switches, Wi-Fi, tablets and printers. | Not checked. | To verify |
| Label printing is on the local network. | Not checked. | To verify |
| The managed backend allows continuous copying of its data (Option 3). | Not checked. | To verify |

Prepared for leadership discussion regarding Warehouse Wizard hosting and continuity. Estimates are budgetary, priced at $100 per hour with an 8-hour day.